## Project Timeline
Studio Project 4 (Team 04) |  |  |  | 2015-02-16 | [9 empty] | 2015-03-15
Deliverables |  | Duration | Name | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 2 | 3 | 4 | 5 | 6
1 | Buildings | 3 Days | Raynold |  |  |  | CNY | [6 empty] | Debug
2 | Multiplayer Mode | 5 Days | Raynold
3 | Pathfinding | 6 Days | Ryan
4 | Fog Of War | 1 Day | Ryan
5 | Levels | 1 Day | Ryan
6 | Player AI | 6 Days | Wei Jie
7 | Animation / Sprites | 2 Days | Wei Jie
8 | Units | 5 Days | Zoe
9 | Resources | 1 Day | Zoe
10 | Power-ups | 2 Days | Zoe
11 | User Interface | 5 Days | Gabriel
12 | Database | 3 Days | Gabriel